## Project Information
REQUIREMENTS ANALYSIS: PROJECT INFORMATION
Project Name: | MERCHANT CASH ADVANCE
Agency: | IT ATLANTIS
Project Sponsor: | VICTOR JOSE AND JUAN TAVARES
Project Manager: | BHAVNEET KUMAR
Last Revision Date: | June 3rd 2014, 9:40pm
Document Status: | DRAFT
Prepared By: | MANMIT WALIA
RAYAN CHANDRA
SAMUEL RAMIREZ
LUCAS MEJIA
Document Scope: | To define a consistent set of requirements for the solution to the MCA project and to identify what is in and out of scope. This document summarizes the requirements gathered in a series of BRD sessions that were conducted by members of the project team.

## In Scope
IN SCOPE REQUIREMENTS
Type | Business Function / Category | Type | ITA Comment | Client Feedback | Priority
Operational | CRM Integration | Question | When will new leads be sent from SF.com to MCA? | When the lead fills the application from and is converted into a Merchant in SalesForce. This is when a lean is converted in EIS. All converted leads should be imported, once imported on the List of Merchants pending for review, if we search and find an existing merchant this pending item can be deleated and stated a status of duplicate.
Operational | CRM Integration | Question | When a lead is sent to the MCA application, who then owns the record? | The same Sales Representative that owned the lead.
Operational | CRM Integration | Question | Will there be a flag in SF.com which we need to look for that will determine which record to sync? | No. All merchants and offers should be synced during the Prequal Workflow. During the contract workflow contract status should bee fed into salesforce as well as the final funded amount.
Technical | Profile Management | Question | What are the fields that needs to be used to gather merchant information manually? | First step has to be search if this reccord already exists, to search it can be done by RNC, Merchant Name, Processor Afiliate Number, Owner Id Number or Owner last name. If no reccord were found a popup could come up that asks "would you like to create a new merchant" when yes, the required information to add this merchant to the queue would be Merchant Name and Sales Rep. Then all the other information will be filled manually in the Data Entry.
Technical | CRM Integration | Question | Will SF mimic the fields for the MCA merchant setup or will there be a screen reference (i.e. iFrame)? | SF will be adapted to the new system, so that it has the same fields.
Technical | Profile Management | Question | What happens when someone tries to create a new lead (manual or SF.com) which already exists? | When the search generates an existing merchant the rep can select the merchant they want to re-evaluate.
Functional | User Interface | Question | How do you imagine the upload document process to work? | Whatever way you see fit, as long as it lets us upload and display the files.
Functional | User Interface | Question | What is the role of other buttons on Scan Doc screen? | They are just for references, you can use the buttons you need to as long as we can upload and display the files. And erase and replace files already uploaded.
Functional | User Interface | Question | Do we have to apply any permissions/role based security to add/view notes on each step? | No. Anyone can write and read notes.
Technical | CRM Integration | Question | Does the SF sales rep needs to be passed to MCA when the record gets sent? | Yes, the same sales reps that owns the SF lead will own the MCA record. They should appear in MCA in the field named salesrep, but this does not mean they are the ones who will be working the workflows
Operational | Synchorinzation | Question | There is integration with Cardnet and Visanet today. How do you guys plan on having the CSV feed generated, sent and loaded? | The files that are sent to the processors with requests and the answers from the processors are uploaded to a FTP site.
Operational | User Interface | Question | Can you provide us an English version of the calculator XLS document? | The file is in English.
Functional | Offer Structure | Question | How can we genrate multiple offers from calculator? | We move the sliders until we are comfortable with an offer and then click save, which will store the current parameters that are on the calculator as an offer. Then if we go ahead an move the sliders again and click save again it will save a second offer and so on.
Functional | Offer Structure | Question | In case decline by Avanzame, do we need to send any notification to customer? | This is where we will model the decline letter and will be sent to the email the customer provided as well as sent to the sales rep, sales manager, also any other email address could be included manually.
Operational | Profile Management | Question | What are preconditions for merchant to appear in Initial queue. | Any converted lead that has filled the application form or that has been included manually in the workflow.
Operational | Profile Management | Question | Select merchant will be manual process or some job/scheduler schedules/assigns merchants to user. | It should be asigned autoamticly depending on what user has these tasks asigned in their workflow profile priverlages.
Operational | Workflow | Question | System assigns ID number to Merchant after review starts what will be identification of merchant entity before review starts | The system should assigen once imported from salesforce, this way this number could be fed immediately back to salesforce so when changes are made in the data entry salesforce knows who to asign to.
Functional | Workflow | Question | What will be criteria to identify merchant being recreated, I mean what all information will be used to check if incoming merchant is a new or existing merchant in system. | First step has to be search if this reccord already exists, to search it can be done by RNC, Merchant Name, Processor Afiliate Number, Owner Id Number or Owner last name. If no reccord were found a popup could come up that asks "would you like to create a new merchant" when yes, the required information to add this merchant to the queue would be Merchant Name and Sales Rep. Then all the other information will be filled manually in the Data Entry.
Functional | Profile Management | Question | If we add merchant manually do we need to check if merchant exists in system. If yes, Where this check will be performed and how(manual or automated check). | First step has to be search if this reccord already exists, to search it can be done by RNC, Merchant Name, Processor Afiliate Number, Owner Id Number or Owner last name. If no reccord were found a popup could come up that asks "would you like to create a new merchant" when yes, the required information to add this merchant to the queue would be Merchant Name and Sales Rep. Then all the other information will be filled manually in the Data Entry.
Functional | Workflow | Question | Will upload application form a mandatory document to upload? | Yes, the Form is a mandatory upload.
Operational | Workflow | Question | TO whom documents will be linked, to merchants or to their contracts? | Application form to the merchant, there are some specific documents during the contract workflow that should be assiged to the contract.
Operational | Workflow | Question | How documents will be saved in database? Or on File system. | I'm not exactly sure about the datbase part, but we should be able to access those documents from the Merchant Profile Screen. There should be a tab that’s called documents and there we should find all the documents that have been uploaded for this merchant
Operational | Workflow | Question | What is “Name of Company” and “Name of Business” and how they are related? | The name of the company is the legal name of the company that owns the business and the name of the business is the name the business uses for its operations. For example, Company A could own Restaurant Food, but it could also own Store One, which would be created as a separate merchant. So we would have two merchants, Store One and Restaurant Food, owned by the same company. This is called affiliations, and affiliation is when a Legal Name has more than one business. this way we can search a merchant by affiliations to see all their related buisness and performance.
Functional | User Access | Question | Will all users have access to modify information on DE page? | No, because not all users should be able to kick start the Workflow. So the permission issues should be adjusted even before the workflow begins.
Functional | Workflow | Question | In case someone changes in DE page, do we keep history, log of changes. | Not neccesary on the DE page. But once the merchant is created any change that we do on the merchant profile has to be logged.
Functional | Workflow | Question | Can all fields be changed? | Yes.
Functional | Workflow | Question | Will there be any validation on DE page. | Please refrase question.
Functional | Profile Management | Question | Is there a format for RNC number? | Just maximum 11 numbers.
Functional | Workflow | Question | What does affiliate number means and how it affects merchant(s)? | This is the number the Processor company identifies the business with. It affects the Merchant because the Processor Company will send us CC sales for that number exclusively, and it is through that number(s) we would be taking payments. We could add more than one processor number for more than one processor.
Functional | Profile Management | Question | Can there be multiple owners of associated with a merchant? | Yes.
Functional | Profile Management | Question | Merchant/Business address mentioned is only one, Will there be any scenario of multiple addresses? | No, because we treat different locations as different business and, as such, different merchants. There could be an office address for the business, for example if an owner has 4 stores but his office address from where he runs his operations is another one, we will need this address in the system. Most of the times it is the same one, but sometimes its different. It could be divided in 2: physical merchant address, billing office address. There should be a button to copy the same physical merchant address in the billing address.
Functional | Profile Management | Question | Will there be any validation on Addresses, Zip Codes etc.? | No
Functional | Workflow | Question | How owner is associated to a Merchant? | The owner is the person (or more than one) who legally own the business. They will sign the contracts.
Operational | Workflow | Question | What will be the trigger point of checking Credit Card volumes from VisNet/CardNet? | Once they arrive they should be tied to the merchant account.
Functional | Workflow | Question | What will be period of Credit Card volumes to be collected? | As much as the Processor company sends. Visanet usually sends no more than 12 months, but cardnet has sent more than 20 months of data.
Functional | Workflow | Question | How CC volumes affect scoring of a merchant? | That depends on the scoring model we end up using, but the CC Volumes are the main input in the scoring model
Technical | Workflow | Question | What is MRF file? Can we get explanation of its content and use? | It's where we send the request for the CC volumes to the Processor company. You'll find a thorough explanation in the file named Processor Files in the bootcamp.
Technical | Workflow | Question | How Credit Card Processor Company works? Is there a Web API? | We send information back and forth through several types of files thru an FTP server. You'll find a thorough explanation in the file named Processor Files in the bootcamp.
Operational | Workflow | Question | Will we send Application form to CardNet? | Yes, but exclusively to CardNet. This part we hven't figure out completely yet, but is something to keep in mind. Visanet does not yet require that we send the forms to them, but cardnet does.
Functional | Workflow | Question | Will Scoring be a manual task? | There will be a Merchant Evaluation task where we will click a button and the system will assign a score to the merchant through whatever score model we end up using. In this same task, is where we pull the credit reports and the system should store them to a document
Functional | Profile Management | Question | What is Datacrédito report? How it will be used to evaluate a merchant? | The Datacrédito report is the credit report for the Company that owns the merchants. It has information on the credit history of the Company and the owner
Functional | Workflow | Question | If we change Gross Yearly Sales Volumes for a merchant in Offer Screen will it be updated in Merchant details? | Yes.
Functional | Workflow | Question | Will it be possible to generate different Offers with different Gross Yearly Sales Volumes or it should be fixed for all offers? | No, he Gross Yearly Sales are tied to the Merchant. A good thing to have is a log when this field gets updated
Functional | Workflow | Question | What is retention percentage and how it affects contract? | It is the percentage of the credit card sales we take as payment. It mary vary depending on the ratio of CC vs total sales
Functional | Workflow | Question | System will be sending emails to SalesRep on both Offer Generation and Denial. Please Confirm. | Yes. It also sends it to a specific group of emails such as the sales manager, underwriting manager, general manager and ops team, as well as any manually enterd email
Functional | User Access | Question | Which Roles/Users can generate Offers? | Underwriters and Renewal agents, also any admin user.
Functional | Offer Structure | Question | Will Contract be queued for Offer generation Officer? | All offer generation task is piled up in a queue that will be asiged automaticly to the person (or more than one) who have this workflow task asigned to their profile. All tasks should be stamped on the time they fall into the workflow and the time that are completed for us to be able to measure efficiencys.
Functional | Offer Structure | Question | If an offer has expired, Do we need to re-score merchant and create a new contract? | If the last scoring is less than 60 days prior to when revaluating, we can reactivate this merchant, if not it has to go thru the complete PQ workflow once again.
Operational | Offer Structure | Question | Will there be any notification for expired Offers? | Yes, maybe an email when the offer expires.
Functional | Offer Structure | Question | What all offer parameters can be changed before accepting it? If an offer parameter is changes do we need to track history of changes? Do we need Merchant consent logged in any form before freezing Offer change? | In the prequal offer everything could be changed thrue the calculator and if applies. We don't need Merchant's consent to change it. It would be good to keep track of the changes.
Functional | Workflow | Question | If a merchant has been created by SalesRep abc but abc did not work on it further what will be the time constraint for second Sales rep to start working on it? | No, same salesrep unless manually changed.
Functional | Workflow | Question | Gross Annual Sales volume check; Should be implemented in Sales force? Just a thought. | No
Functional | Workflow | Question | Can a merchant be associated to 2 sales representatives? | Yes
Functional | Workflow | Question | Document did not show any association between Sales Rep and Merchant. Is there anyway a Sales Rep affects Offers/Merchant? | The Merchant is assgined to the Sales Rep, but otherwise it won't affec the logistics, offers have no impact whatsoever upon what sales rep it is asigend to.
Functional | Workflow | Question | How decline by client reasons affect a contract? | We have detailed decline reasons just for informational purposes.
Functional | Workflow | Question | Is there a restriction on steps to be Kicked Back? What all steps can be Kicked back and up to which step a kick back can be done. | No restrictions, a kick back can be done from any task to any previous task.

## Out Scope
OUT OF SCOPE REQUIREMENTS
Type | Business Function / Category | Type | ITA Comment | Client Feedback | Priority

## Definitions
Definition of 'Type'
Term | Definition | Example Considerations
Functional | Impacts the Business Process Requirements that define those features of the product that will specifically satisfy a Consumer need, or with which the Consumer will directly interact. | -Common Functions -GUI Functions -Reporting Functions -Interface Functions -Batch Functions -Security Functions
Technical | Impacts the Product Infrastructure Requirements that identify the technical constraints or define conditions under which the product must perform. | -Accessibility -Encryption -Hosting -Environment -Disaster Recovery
Operational | Impacts Operations and Support Requirements that define those "behind the scenes" functions that are needed to keep the product operational over time. | -System Performance -Data Archival -Audit and Controls -System Administration -System Quality Assurance -Business Continuity
Transitional | Impacts Implementation Requirements that define those aspects of the product that must be addressed in order for the product to be successfully implemented and to relegate support responsibilities to the Performing Organization. | -Data Conversion -Release Validation -Documentation -Training -Deployment
Definition of 'Business Function / Category'
Term | Definition
Business Function / Category | The business function column is used for ‘Functional’ types of requirements. The purpose for the column is to categorize the requirements, which in turn helps the team ensure that they have captured all of the requirements for a given business function. Example: An insurance program may have business functions of: benefits, appeals, adjudications, etc. Each of these business functions may have requirements specific to itself.
Definition of 'Priority'
Term | Definition
Core | Requirements without which the product may as well not be developed at all; it will be of no use to most Customers without these.
Essential | Requirements for which a short-term work-around could be developed (or for which an old process can be used for a little while longer), but over the long run, the requirements have to be there.
Desired | Requirements that are the "bells and whistles" which may be precious to certain constituencies, but without which the product will function just fine.
A product must be delivered with all Core and a good portion of Essential requirements represented, and with a plan to implement the remaining Essential requirements in the subsequent phase.

## Look Up Values (hidden)
Transitional | Back Office | Core | Requirement
Technical | CRM Integration | Desired | Question
Operational | Mobility | Essential
Functional | Offer Structure
Profile Management
Reporting
Synchorinzation
User Access
User Interface
Workflow